## Slide 1: Project Data Analysis
Project proposal

## Slide 2: Key Topics
Terms of Reference
Scope and Objectives
Project Methodology and Approach
Risks
Milestone Schedule
Project methodology and Approach
1

## Slide 3: Terms of Reference
Customers want to invest in real estate or the stock market
Customers want software to monitor and predict the market in the coming months
The client
The problems
There are many different types of stocks circulating in the market, so it is difficult for customers to choose to invest. The value of stocks always changes over time, they can increase or decrease
The PDA project will create a website that can predict the stock or housing market based on the collected data set. Based on those predictions, clients can decide which stocks to invest in.
2

## Slide 4
Scope and Objectives
Project Objectives
The purpose of this PDA project is to create a website that shows stock market predictions through various types of graphs
The business goals for this project directly assist the client in predicting the market in the coming months.
Success Criteria
Shows next month's prediction based on previous months.
Must have a UAT version for customers to try before releasing the final version.
The final product must be usable and predictive
3

## Slide 5
Scope
Scope Description
The dataset must come from a trust resource, and the dataset does not need to be changed based on real time
There are documents and sources that prove the predictions are reliable.
Constraints
Costs must not exceed the estimated budget.
The final product must be released within 6 months.
The final product must satisfy the MVP.
4

## Slide 6
Requirements
Functional Requirements
ID | As a | I want to | Therefore
1 | Customer | see the stock market trends | I want a web app to display the graph
2 | Customer | invest in a stock | I want to see algorithm-based market prediction with a presentation of how each algorithm is done
5

## Slide 7
Project methodology and Approach
Vision
To deliver delivered products, we will research algorithms to predict the market based on data sets.
Building a web application to represent the prediction results.
7

## Slide 8
Method and Approach
Apply the Scrum process to manage this PDA project.
Devide the project into four main Pis.
Each PI will be broken down into smaller appropriate Sprints.
Before each Sprint, there will be a planning meeting to divide tasks and have weekly reports.
On average, each sprint will last about 2 weeks.
Scrum
Project Management
Jira will be used as a project management system for the PDA project, including task division, task assignment, and performance tracking, time tracking.
8

## Slide 9
Summary Milestone Schedule
Summary Milestone Schedule – List key project milestones relative to project start. |  | 
Project Milestone | Start Date | Due Date
Project Start |  | October 21st, 2021
PI Planning finish |  | October 30th, 2021
First PI finish |  | December 31st, 2021
Second PI finish |  | February 28th, 2022
Third PI finish |  | March 31st, 2022
Final PI finish |  | April 30th, 2022
Project Complete |  | April 30th, 2022
12

## Slide 10
Project Deliverables
According to each PI, there will be documents that need to be completed
First PI:
  A0100- Analysis Report
  O0500 - Software Architecture - Clarification Phase
Second PI:
  D0100 - User Interface Guidelines
  DD130 - Detailed Design
  D0160 - User Interface Design
  O0500 - Software Architecture
Third PI:
  MVP Version
Fourth PI:
  Final Product
6

## Slide 11
Risk Identification
Risk Identification |  | Qualitative Rating |  |  |  | Risk Response | 
Risk | Risk Category | Probability | Impact | Risk Score | Risk Ranking | Risk Response | Trigger
Human absence due to personal issues | Human Resources | 2 | 3 | 6 | III | Reschedule the tasks or assign them to another member | Team members have to inform all team.
Functions do not meet customers’ requirements. | Stakeholder expectations | 3 | 4 | 12 | IV | Try to negotiate with the stakeholders | Stakeholders' negative feedback
Cannot complete all the requirements on deadline. | Time | 2 | 4 | 8 | III | 1. Inform the stakeholders before the predetermined deadline a week. 2. Working overtime to finish as soon as possible | One week before the deadline, there are still 2 more requirements
Risks
9

## Slide 12
Risks
Risk Identification |  | Qualitative Rating |  |  |  | Risk Response | 
Risk | Risk Category | Probability | Impact | Risk Score | Risk Ranking | Risk Response | Trigger
The conflict between team members leads to inefficient work. | Human Resources | 1 | 2 | 2 | I | 1. Find out the reason 2. Solve the problems | Cannot communicate members when needed
Customers may change requirements during the project. | Scope | 2 | 3 | 6 | III | Depend on the ability of the team developer | Stakeholders inform that they need to modify their requirement(s)
During project development, the interface went wrong with the design. | Technical Accuracy | 2 | 2 | 4 | II | 1. Fix those problems as soon as possible. 2. Define the new design within considering. | The real design is not the same as the design when checking
10

## Slide 13
Skill Analysis
Group | Skill Expertise | Level |  |  |  | 
 |  | 1 | 2 | 3 | 4 | 5
Technical Skill | HTML/CSS |  |  | x |  | 
 | JavaScript |  | x |  |  | 
 | Django |  | x |  |  | 
 | React | x |  |  |  | 
Team Skill | Presentation |  |  |  | x | 
 | Research |  |  |  | x | 
 | Problem Solving |  |  |  | x | 
 | Conflict management |  |  | x |  | 
 | Time managing |  |  |  |  | x
11

## Slide 14
Summary Budget
Summary Budget – List component project costs | 
Project Component | Component Cost
Personnel Resources | $110,000
Hardware | $45,000
Software and Licensing | $75,000
IT Lab Preparation | $15,000
Total | $245,000
13